**Technical Guidance & Consulting Service**

|  |  |  |  |
| --- | --- | --- | --- |
| **Main activity** | **Sub activity** | **Target date** | **remarks** |
| **Technical Guidance & Consulting service** **for** **the local companies near** **Assiut and Upper Egypt** | **Announcement for Applying to this activity** | 2017. 08. 09 | No applications will be received after this date |
| **Successful applicants will submit a contract advisory report with the signature of CEO of the chosen factory** | 2017. 08. 16 | Final date |
| **Finalizing the decision by UICC & SC** | 2017. 08. 17 |  |
| **Notify selected** **the 15 PPs** | 2017. 08. 23 | 15 companies |
| **Advisory visits :****Total 15 companies** | 2017. 08. 25 ~2017. 09. 24 | US$20\*20회 (US$400max)  |
| **Submit full report by the 15 PPs**  | 2017. 09. 26 | 15 Reports from PPs15 Feedback Reports from Companies |
| **Select six reports and send them to Korea****(by UICC & SC)** | 2017. 09. 27 | In case of accepting to increase total number from six to 10 PPs |
| **Finalizing 4 PPs** **(by KOREATECH)** | 2017. 10. 20 | Two months preparation process (VISA and etc) |
| **Travelling to** **KOREATECH/Korea** | 2018. 1. 10 ~2018. 2. 14 | Confirm the VISA Process prior to the departure to KOREATECH/Korea |

**\*Info for the project Homepage/ UICC**